## Sheet1
Project Title: Abundant Futures: College Alternative Resource Site
Milestone | Description of Deliverables | Due Date | Modified Completion Date/Status |  | Comments | Why was Milestone not met?
Project Proposal | A topic had to be chosen and submitted for approval | 2020-09-06 | Completed |  | N/A
Design Review, Tool Selection, Meeting with Professor | A meeting with the professor to discuss tools, SPMP deliverables, and the future progress of project. | 2020-11-16 | Completed |  | Have to clarify and finalize how to get specific information without hardcoding. Use GhitHub student pack for hosting ideas.
Final Deliverable Due Date |  | 2020-11-18 | Completed
Final Presentation Due Date |  | 2020-11-23 | Completed |  | Needs to be updated with new information from presentation
Presentation Day |  | 2020-11-24 | In Progress… (11/24/2020) |  |  | Scheduled to present tomorrow on 11/24/2020
Get API for Scholarships | Find an API to get a list of scholarships being offered | 2020-10-22 | In Progress… (12/1/2020) |  | Need to send and recieve access to Chegg's scholarship API | Underestimated the time it takes to find, request, understand and use an API. Ran out of time to implement.
Get ApI for Vocational School Information | Find an ApI to get vocational Schools listings | 2020-10-22 |  | In Progress… (12/1/2020) | Hard time finding listings or search engines for vocational schools. Plan to use CollegeAI API | Difficult to find vocational school information. I was still adapting, researching and understanding API usage. Took up a lot of time
Get an API for Free College Listings | Find an API to display Free College Listings | 2020-10-22 |  | Completed | Update: Displays low cost colleges
Get API for Career Opportunities | Find an API to find job opportunities and Resume Centers | 2020-10-22 |  | Completed | Update: Not set to display jobs by deault, must enter content in fields.
Learn how to implement Contact form for 'Contact Us' | Create a Contact form to have user enter a message and receive it in database. | 2020-10-30 | In progress… (12/2/2020) |  | Update: Began constuction of the form but it does not send message to admin. Just empty the fields. | Held off until last minute but I got swamped with other class responsiblities at the time. Only had time to implement the basics.
Format each page | Format each page in a presentable manner | 2020-10-30 |  | Completed | Basic Layouts on each page with Logo in top corner and navigation.
Set Links to be directed to each page | When a tab is clicked in navigation, it goes to its corresponding page. | 2020-11-07 |  | Completed
Allow Logo to direct user to homepage | When the Logo is clicked on from any page, the user is directed back to home page. | 2020-11-07 | In Progress… (11/30/2020) |  | Did not have time to implement this feature. | Also held off until last minute, due to setting it as a low-priority feature.
Upload all files to Repo | Upload all deliverables and website files to Ghit Hub. | 2020-11-23 |  | Completed
Testing each page of site | Make sure each page is deployed and running successfully on live site. | 2020-11-22 | In Progress… (12/2/2020) |  | Some data is not finished being implemented on website. | Finding and utilizing the API information for some sites and getting familiar with the code to implement API was new to me. Other class responsibilities started to pick up and I had less time to dedicate toward research.
Completion of Milestone | Submit a milestone report of project | 2020-11-23 |  | Completed